## INSTRUCTIONS
1 | Executive Summaries are due to Mike Heath on the 25th of the following month.
2 | The following should be cc'd on the report: Sr. VP, PEx, Superintendent, Cost Engineer, Sydney Johnian, Ben Lawrence
3 | The purpose of the report is to provide an accurate snapshot of the project as of the date issued. To ensure accuracy and completeness, a monthly project review meeting should be held with the Super, PEx, Sr. VP, Gen Superintendent and any other personnel required to discuss the project. All aspects of the project should be reviewed at a high level including: Latest updated schedule, labor projections for GC and GR items, status of safety, status of quality control program.
4 | Special attention should be paid to this report to advise of any potential issues that may not be immediatey apparent to Sr. Management
5 | Ensure that all subcontractor requisitions and misc invoices are approved and posted to the job cost to ensure the financial information is as accurate as possible.

## COVER
Executive Summary
1 | CONSTRUCTION SCHEDULE |  | #Project Name
| 1.1 | Dates | LKCO Job #:
| 1.2 | Communication of Variance
| 1.3 | Recovery Plan
| 1.4 | Milestones
2 | HOT LIST
3 | PROJECT SAFETY
4 | QUALITY CONTROL |  | Monthly Status Report
#Month, 20XX
5 | FINANCIAL
| 5.1 | Contract Status
| 5.2 | Fee
| 5.3 | General Conditions
| 5.4 | General Requirements
| 5.5 | Contingency
| 5.6 | Allowances
| 5.7 | Related Costs
| 5.8 | PCO's and Owner Changes
| 5.9 | Subcontractor Change Requests
| 5.1 | Purchasing
Attachments:
1 | Latest Project Schedule
2 | Cost Report
3 | Labor Projections Report
4 | Contingency Log
5 | Allowance Log
6 | Related Cost Log
7 | PCO Log
8 | Subcontractor Change Order Log
9 | Purchasing Log
10 | WBE/MBE & Workforce Compliance

## Section 1
Executive Summary
|  |  |  | For Month of: | #Month, 20XX
[6 empty] | LAST MONTH | THIS MONTH | VARIANCE |  | Instructions
1 | CONSTRUCTION SCHEDULE
1.1 | Dates
|  | Original Substantial Completion Date |  |  | 0 |  |  |  |  | NOTE:--date entry format is "3/12/21"
|  | Current Projected Substantial Completion Date |  |  |  | 0 | 0 | 0 | cal days
|  | Variance from Original Date |  |  |  | 0 | 0 |  | cal days
1.2 | Communication of Variance
|  | explanation of variances | [7 empty] | This should be a full explanation of what issues are impacting the schedule. Note--not limited to space size…write as much information as necessary to explain and document what is happening.
1.3 | Recovery Plan
|  | explanation | [7 empty] | This should be a full explanation of what needs to be done to rectify the issue and whether costs are associated with it or not.
1.4 | Milestones | [8 empty] | Provide detailed list of milestones that the team is focused on that are critical to the success of the project.
Milestones for the next quarter
|  | Month DD, YYYY | Milestone Description
|  | Month DD, YYYY | Milestone Description
|  | Month DD, YYYY | Milestone Description
|  | Month DD, YYYY | Milestone Description
2 | HOT LIST
|  | explanation | [7 empty] | This should be a full explanation of what issues are impacting the project--both internally and externally--what is "HOT" that if not resolved quickly is going to impact the project.
3 | PROJECT SAFETY
|  | describe any safety issues/incidents that have occurred, how have inspections been the last month and what are the top focus areas on the project regarding safety | [7 empty] | Explain how the project is being managed in terms of safety--note whether all required monthly inspections are being performed. Then dig into the data and explain what the negative themes are and what is the team doing to correct them?
4 | QUALITY CONTROL
|  | describe status of project in relation to QA/QC over the last 30 days. Have inspections been conducted and have they revealed any issues? What subs have had kickoff meetings with in the last 30 days, what is upcoming over the next month with regards to QA/QC? | [7 empty] | Report on the overall QA/QC process. Note what is going well and what needs to be improved on the project. Note what trades are mobilizing in the next 30 days--confirm kick off meetings are happening, etc…
5 | WBE/MBE and Workforce Tracking
Describe the status of WBE/MBE participation as well as workforce compliance in regards to the BRJP or other contractual requirements. Attach latest report as applicable.

## Section 2
|  |  | Executive Summary | [7 empty] | Instructions
|  |  |  | For Month of: | #Month, 20XX | [5 empty] | Note that the report is for the previous month: ie if report is being issued on July 25th, the report is for JUNE.
MONTHLY
[6 empty] | LAST MONTH |  | THIS MONTH | VARIANCE | Notes
5 | FINANCIAL | [9 empty] | NOTE: if field is not highlighted, it is a formula. Only enter information into highlighted fields
5.1 | Contract Status
|  | Original Contract Value |  |  | 0
|  | Current Budget |  |  |  | 0 |  | 0 | 0
|  | Latest Change Order Number Executed |  |  |  | 0 |  | 0
|  | Total Cost to Date |  |  |  | 0 |  | 0 |  |  | This is from the "Actual Cost " column on the cost report
|  | Current Contract Sum (line 3 on G702) |  |  |  | 0 |  | 0 | 0 |  | This is from line 3 of the Requisition cover sheet
|  | Requisition-Total Completed and Stored To Date |  |  |  | 0 |  | 0 | 0 |  | This is from line 4 of the Requisition cover sheet
|  | Date requisition was sent to owner |  |  |  | 0 |  | 0 |  |  | NOTE:--date entry format is "3/12/21"
|  | Over/(Under) billed |  |  |  | 0 |  | 0
|  | Projected Project Cost as of 12/31 |  |  |  | 0 |  | 0 | 0 |  | Input value based on cash flow projections as of 12/31 of current year
|  | Anticipated % Complete as of 12/31 |  |  |  | #DIV/0! |  | #DIV/0! |  |  | Percent Complete based on estimate above
5.2 | Fee
|  | LKCO's percentage of shared savings: | [8 empty] | Enter the percentage of shared savings if applicable..or "N/A"
|  | Original Fee |  |  | 0 | [5 empty] | This if the "original budget amount" line on the cost report for code 99-00501.00
|  | Fee adjustment from change orders |  |  |  | 0 |  | 0 | 0 |  | Sum of all fee included in executed Owner Change Orders
|  | Fee adjustment from General Conditions |  |  |  | 0 |  | 0 | 0 |  | Input value from row 40 if LUMP SUM GC's
|  | Fee recognized from Shared Savings through executed OCO |  |  |  | 0 |  | 0 | 0 |  | Enter a value here only if this fee has been realized from an OCO
|  | Additional anticipated fee from shared savings | [8 empty] | Enter value here if additional savings in the GMP are anticipated to be realized
|  | Fee adjustment from Incentives |  |  |  | 0 |  | 0 | 0 |  | Enter a value here for any incentives that have been realized
|  | Fee adjustment from other (Specify) |  |  |  | 0 |  | 0 | 0 |  | Enter a value here and provide a note indicating what the fee enhancement is generated from (rarely used)
|  | Current Projected Fee |  |  |  | 0 |  | 0 | 0 |  | This is a formula.
5.3 | General Conditions
|  | Lump Sum? |  |  | Yes/No | [5 empty] | Enter either "yes" or "no" if the project is subject to lump sum GC's
|  | Original Budget |  |  | 0 | [5 empty] | This is the value from the "original budget amount" line in the cost report
|  | Current Budget |  |  |  | 0 | 0 | 0 |  |  | This is the value from the "current budget" column on the cost report
|  | Actual Cost |  |  |  | 0 |  | 0 | 0 |  | This is the value from the "Actual Cost" column on the cost report
|  | Cost to Complete |  |  |  | 0 |  | 0 | 0 |  | This is the value should include the total of the "Remaining Committed Costs" plus the "Cost to Complete" columns on the cost report
|  | Cost at Completion |  |  |  | 0 |  | 0 | 0 |  | This is a formula and should match the "cost at completion" on the cost report
|  | Completion Variance |  |  |  | 0 |  | 0 | 0 |  | This is a formula and should match the "completion variance" on the cost report
5.4 | General Requirements
|  | Original Budget |  |  | 0 | [5 empty] | This is the value from the "original budget amount" line in the cost report
|  | Current Budget |  |  |  | 0 |  | 0 |  |  | This is the value from the "current budget" column on the cost report
|  | Actual Cost |  |  |  | 0 |  | 0 | 0 |  | This is the value from the "Actual Cost" column on the cost report
|  | Remaining Committed |  |  |  | 0 |  | 0 | 0 |  | This is the value of the "Remaining Committed Costs" on the cost report
|  | Cost to Complete |  |  |  | 0 |  | 0 | 0 |  | This is the value of the "Cost to Complete" column on the cost report
|  | Cost at Completion |  |  |  | 0 |  | 0 | 0 |  | This is a formula and should match the "cost at completion" on the cost report
|  | Completion Variance |  |  |  | 0 |  | 0 | 0 |  | This is a formula and should match the "completion variance" on the cost report
|  | Progress Cleaning Cost at Completion (enter the variance shown in cost report) |  |  |  | 0 |  | 0 | 0 |  | Enter the value from the "completion variance" for the progress cleaning cost code
5.5 | Contingency
|  | Original Contingency |  |  | 0 | [5 empty] | Enter values for this section from the Construction Contingency Cost Code. Typically 99-5050.00
|  | Committed Contingency |  |  |  | 0 |  | 0 | 0
|  | Projected Contingency Expenditures |  |  |  | 0 |  | 0 | 0
|  | Remaining Contingency |  |  |  | 0 |  | 0 | 0
5.6 | Allowances | [9 empty] | Enter values for this section from all AIA Allowances that are defined in the Owner Contract. The values should match the Allowance Log attached to the cost report.
|  | Original Allowances |  |  | 0
|  | Committed Allowances |  |  |  | 0 |  | 0 | 0
|  | Remaining Allowance Value |  |  |  | 0 |  | 0 | 0
5.7 | Related Costs | [9 empty] | Enter values for this section from all of the various related costs that have been developed either at the time of the GMP or as the project buyout was completed and should match the Related Cost Log attached to the report
|  | Original Related Costs |  |  | 0
|  | Committed Related Costs |  |  |  | 0 |  | 0 | 0
|  | Remaining Allowance Value |  |  |  | 0 |  | 0 | 0
5.8 | PCO's and Owner Changes | [9 empty] | This information comes from all events being tracked through the Change Management process and should match the PCO log attached to the cost report.
|  | Total of PCO's Submitted and Not Approved |  |  |  | 0 |  | 0 | 0
|  | Total PCO's Pending and Not Submitted |  |  |  | 0 |  | 0 | 0
5.9 | Subcontractor Change Requests | [9 empty] | This information comes from the subcontractor change request logs and should include any work done on Time and Material as well as any claims submitted.
|  | Total Subcontractor Change Requests outstanding |  |  |  | 0 |  | 0 | 0
|  | Total Subcontractor Change Requests not accounted for in PCO |  |  |  | 0 |  | 0 | 0
5.1 | Purchasing | [9 empty] | This information comes from the Buyout log provided by the Estimating Department which should be attached to the cost report.
|  | Total Subcontract Value to be purchased |  |  |  | 0 |  | 0 | 0
|  | Total Value of subcontracts actually purchased |  |  |  | 0 |  | 0 | 0
|  | Total Buyout Savings/(Overrun) to Date |  |  |  | 0 |  | 0 | 0
|  | Total Value of remaining subcontracts to purchase |  |  |  | 0 |  | 0 | 0