## March 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-02-28 | Pencil requisition submitted
2023-03-10 | Final requisition due
2023-03-12 | All subcontractor requisitions/misc invoices approved
2023-03-15 | First draft of cost report due to PX/VP
2023-03-15 | Final cost report due: Interiors/ Special Projects
2023-03-21 | Final cost report due: General Construction
2023-03-22 | Cost report due to CFO
2023-03-28 | Monthly analytics issues by cost controller
March 23-30 | Monthly cost report review meeting

## April 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-03-30 | Pencil requisition submitted
2023-04-10 | Final requisition due
2023-04-12 | All subcontractor requisitions/misc invoices approved
2023-04-15 | First draft of cost report due to PX/VP
2023-04-15 | Final cost report due: Interiors/ Special Projects
2023-04-21 | Final cost report due: General Construction
2023-04-22 | Cost report due to CFO
2023-04-28 | Monthly analytics issues by cost controller
April 23-April 30 | Monthly cost report review meeting

## May 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-04-30 | Pencil requisition submitted
2023-05-10 | Final requisition due
2023-05-12 | All subcontractor requisitions/misc invoices approved
2023-05-15 | First draft of cost report due to PX/VP
2023-05-15 | Final cost report due: Interiors/ Special Projects
2023-05-21 | Final cost report due: General Construction
2023-05-22 | Cost report due to CFO
2023-05-28 | Monthly analytics issues by cost controller
May 23-May 30 | Monthly cost report review meeting

## June 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-05-30 | Pencil requisition submitted
2023-06-10 | Final requisition due
2023-06-12 | All subcontractor requisitions/misc invoices approved
2023-06-15 | First draft of cost report due to PX/VP
2023-06-15 | Final cost report due: Interiors/ Special Projects
2023-06-21 | Final cost report due: General Construction
2023-06-22 | Cost report due to CFO
2023-06-28 | Monthly analytics issues by cost controller
June 23-June 30 | Monthly cost report review meeting

## July 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-06-30 | Pencil requisition submitted
2023-07-10 | Final requisition due
2023-07-12 | All subcontractor requisitions/misc invoices approved
2023-07-15 | First draft of cost report due to PX/VP
2023-07-15 | Final cost report due: Interiors/ Special Projects
2023-07-21 | Final cost report due: General Construction
2023-07-22 | Cost report due to CFO
2023-07-28 | Monthly analytics issues by cost controller
July 23-July 30 | Monthly cost report review meeting

## August 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-07-30 | Pencil requisition submitted
2023-08-10 | Final requisition due
2023-08-12 | All subcontractor requisitions/misc invoices approved
2023-08-15 | First draft of cost report due to PX/VP
2023-08-15 | Final cost report due: Interiors/ Special Projects
2023-08-21 | Final cost report due: General Construction
2023-08-22 | Cost report due to CFO
2023-08-28 | Monthly analytics issues by cost controller
August 23-August 30 | Monthly cost report review meeting

## September 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-08-30 | Pencil requisition submitted
2023-09-10 | Final requisition due
2023-09-12 | All subcontractor requisitions/misc invoices approved
2023-09-15 | First draft of cost report due to PX/VP
2023-09-15 | Final cost report due: Interiors/ Special Projects
2023-09-21 | Final cost report due: General Construction
2023-09-22 | Cost report due to CFO
2023-09-28 | Monthly analytics issues by cost controller
September 23-September 30 | Monthly cost report review meeting

## October 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-09-30 | Pencil requisition submitted
2023-10-10 | Final requisition due
2023-10-12 | All subcontractor requisitions/misc invoices approved
2023-10-15 | First draft of cost report due to PX/VP
2023-10-15 | Final cost report due: Interiors/ Special Projects
2023-10-21 | Final cost report due: General Construction
2023-10-22 | Cost report due to CFO
2023-10-28 | Monthly analytics issues by cost controller
October 23-October 30 | Monthly cost report review meeting

## November 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-10-30 | Pencil requisition submitted
2023-11-10 | Final requisition due
2023-11-12 | All subcontractor requisitions/misc invoices approved
2023-11-15 | First draft of cost report due to PX/VP
2023-11-15 | Final cost report due: Interiors/ Special Projects
2023-11-21 | Final cost report due: General Construction
2023-11-22 | Cost report due to CFO
2023-11-28 | Monthly analytics issues by cost controller
November 23-November 30 | Monthly cost report review meeting

## December 2023
Due Date | Activity | Completed (Y/N) | Additional Notes
2023-11-30 | Pencil requisition submitted
2023-12-10 | Final requisition due
2023-12-12 | All subcontractor requisitions/misc invoices approved
2023-12-15 | First draft of cost report due to PX/VP
2023-12-15 | Final cost report due: Interiors/ Special Projects
2023-12-21 | Final cost report due: General Construction
2023-12-22 | Cost report due to CFO
2023-12-28 | Monthly analytics issues by cost controller
December 23-December 30 | Monthly cost report review meeting